## General
Team Number: | Phuket List
Week: | 12

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | To implement features of friend request and messages.
2 | Improve front end components for user profile page.
3 | Begin environment configurations for front end and back end.
4
5
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | None
2
3
4
5
C. | List your accomplishments from the previous week
1 | Improved front end for user profile page and activity page.
2 | Use cloudinary service to upload images faster.
3
4
5
6
7
8